## README
Workbook | MCE Command Center – Planning Pack (v1)
Created | 2025-12-20 00:21
Purpose | Single place to capture uncertainties/assumptions, requirements, document taxonomy, and the 2-week quick-win plan.
How to use | Fill/adjust rows marked HITL=Yes. Keep IDs stable; add new rows at bottom. Use Requirements_Checklist to mark MVP scope.
Owner | Moe (Super Admin / Program Owner)
Notes | This file is designed to be updated iteratively as more documents are ingested (Claude Code skills, policies, RFPs, proposals).

## Uncertainty_Log
ID | Area | Uncertainty | Impact | Confidence_% | Evidence_needed | Proposed_assumption | HITL | Owner | Decision_deadline | Notes
U-001 | Org/People | Exact departments + heads + reporting lines (incl. tender committee) | High | 35 | Org chart + RACI | Assume: Mgmt, PMO, Arch, MEP, Structural, QS/Cost, Finance, HR, IT, BD, QA/QC, Compliance | Yes | Moe | 2025-12-22 | Needed to set RBAC + routing.
U-002 | Systems | Current systems inventory (QuickBooks version, file server/SharePoint/OneDrive, email platform, tender portals) | High | 30 | IT stack list | Assume: O365 email, shared drives/SharePoint, QuickBooks (desktop), basic NAS backups | Yes | IT Lead | 2025-12-22 | Integration scope + connectors.
U-003 | Security | Data residency constraints (cloud allowed? UAE-only? healthcare data constraints) | High | 25 | IT + legal note | Assume: default on-prem/UAE hosting option required; cloud optional with approval | Yes | Compliance | 2025-12-22 | Affects hosting + RAG.
U-004 | Legal | Which projects are under DOH/ADHICS or other sector rules (health data) | High | 40 | Project list + client sector | Assume: healthcare-heavy portfolio; treat all project docs as Confidential by default | Yes | Compliance | 2025-12-27 | Applies stronger controls.
U-005 | Ops | Tender intake process: who receives first email + how docs are stored today | High | 45 | Process walkthrough | Assume: centralized tender mailbox + manual foldering | Yes | BD/PMO | 2025-12-22 | Defines ingestion automation.
U-006 | Ops | Tender participation decision SLA and gatekeepers | High | 40 | Mgmt policy or practice | Assume: VP/Chairman approval required within 24–48h of receipt | Yes | Management | 2025-12-22 | Drives notification escalation.
U-007 | Data | Canonical project stages (Design vs Supervision vs Pre-Concept) and sub-stages | High | 50 | Current tracker or list | Assume: Pre-Concept→Concept→Schematic→Detailed→Tender→Construction Support→DLP | Yes | PMO | 2025-12-27 | Needed for tracker schema.
U-008 | Data | Tender stages and required artifacts per stage | High | 50 | Past tender log | Assume: Intake→Eligibility→Clarifications/RFI→Site Visit→Tech→Commercial→Submission→Follow-up→Award/Regret | Yes | PMO | 2025-12-27 | Needed for KPI + workflow.
U-009 | Notifications | Preferred channels for alerts (email/Teams/WhatsApp/SMS) and escalation hierarchy | High | 45 | Mgmt preference | Assume: email + in-app now; Teams later; SMS only critical | Yes | Management | 2025-12-22 | Must be right early.
U-010 | Docs/RAG | Preferred RAG boundary: per-client, per-project, or global + filtered? | High | 35 | Policy decision | Assume: global index with strict tenant/project filters; optional isolated vaults | Yes | Compliance | 2025-12-27 | Avoids leakage.
U-011 | Docs/RAG | Accepted doc parsing stack (Docling vs Unstructured vs Azure Form Recognizer etc.) | Med | 60 | PoC results | Assume: Docling first; fall back to Unstructured for edge cases | No | Engineering | 2025-12-27 | Can change after PoC.
U-012 | UI | Ed Hounour-style tracker UI elements that must be replicated (views/fields) | Med | 55 | Screenshot/examples | Assume: table + kanban + status chips + quick filters + weekly focus view | Yes | Moe | 2025-12-27 | Affects UX acceptance.
U-013 | Finance | 30/60/90 forecast model: what inputs exist today? | High | 30 | Finance workbook/process | Assume: invoices + expenses in QuickBooks; need export to CSV | Yes | Finance | 2025-12-27 | Later module but needs schema now.
U-014 | Email | Email analysis scope: read-only classification vs auto-drafting vs auto-sending | High | 35 | Policy decision | Assume: drafting + human send (HITL) for v1; read-only ingestion ok | Yes | Compliance | 2025-12-27 | High risk area.
U-015 | Deployment | Target hosting: on-prem server, UAE cloud VM, or managed PaaS? | High | 40 | IT decision | Assume: Docker Compose on UAE VM for v1; k8s later | Yes | IT Lead | 2025-12-22 | Impacts bootstrap.
U-016 | Docs/RAG | Bilingual handling: Arabic/English docs + mixed tables | High | 40 | Sample bilingual docs | Assume: store original + normalized bilingual metadata; bilingual embeddings if needed | Yes | Engineering | 2025-12-27 | Impacts search quality.
U-017 | Docs/RAG | What constitutes an acceptable citation (page/section) for management | Med | 55 | Stakeholder examples | Assume: page+clause refs in outputs mandatory | Yes | Management | 2025-12-27 | Trust requirement.
U-018 | Docs/RAG | Allowed LLM providers for sensitive data (OpenAI/Anthropic/on-prem) | High | 25 | Policy decision | Assume: run sensitive inference on approved provider; allow local models for Restricted | Yes | Compliance | 2025-12-22 | Critical.
U-019 | Ops | Standard tender folder naming convention | Med | 60 | Current folder examples | Assume: {YEAR}-{CLIENT}-{TENDERREF}-{TITLE} | Yes | PMO | 2025-12-27 | Automation depends on this.
U-020 | Ops | Document versioning approach (v1/v2 vs git-like) | Med | 55 | SOP | Assume: semantic version + audit trail; keep originals immutable | Yes | QA/QC | 2025-12-27 | Avoid confusion.
U-021 | Ops | Who owns tender templates today and approval authority for new ones | High | 45 | Mgmt decision | Assume: PMO owns; Dept heads approve; VP final | Yes | Management | 2025-12-27 | Template governance.
U-022 | Ops | Required tender deliverables checklist varies by client? | High | 50 | Past submissions | Assume: base checklist + client overlays | Yes | PMO | 2025-12-27 | Model needs rules.
U-023 | Ops | RFI process: who drafts, who approves, where logged | High | 45 | Process map | Assume: PMO drafts; discipline inputs; VP approves | Yes | PMO | 2025-12-27 | Automation scope.
U-024 | Projects | DLP definition and tracking approach (some clients differ) | Med | 55 | Contract examples | Assume: DLP end date is contract-defined; store per project | Yes | PMO | 2025-12-27 | Tracker must handle.
U-025 | Projects | Milestone taxonomy: approvals, submissions, inspections, permits | High | 45 | Sample schedules | Assume: milestone types list with required fields + owners | Yes | PMO | 2025-12-27 | Alert engine input.
U-026 | Security | Audit log retention period requirement | High | 35 | IT/Compliance requirement | Assume: 5 years retention with tamper-evident storage | Yes | Compliance | 2025-12-27 | Compliance.
U-027 | Security | MFA requirement for admin roles | High | 60 | Policy decision | Assume: MFA mandatory for Super Admin/Management | Yes | IT Lead | 2025-12-27 | Hardening.
U-028 | Security | External sharing policy (subconsultants) | High | 40 | SOP | Assume: time-bound links + watermark + NDA flag | Yes | Management | 2025-12-27 | Doc sharing.
U-029 | Integrations | Teams/SharePoint vs file server: primary document store | High | 35 | IT decision | Assume: SharePoint/OneDrive as primary if available | Yes | IT Lead | 2025-12-22 | Impacts storage APIs.
U-030 | Integrations | Tender portal list (ADAFSA, DOH, etc.) + access method | Med | 45 | Portal list | Assume: manual portal interaction; log only in MVP | Yes | BD | 2025-12-27 | Future automation.
U-031 | Performance | Target max time to generate tender summary report | Med | 55 | Mgmt expectation | Assume: <10 min for typical pack; <30 min for large | Yes | Management | 2025-12-27 | NFR.
U-032 | Performance | Max document size for upload (zip/pdf) | Med | 60 | IT constraints | Assume: 500MB per tender pack for MVP | No | Engineering | 2025-12-27 | Tune later.
U-033 | UI/UX | Required views: table vs kanban vs calendar vs Gantt | Med | 55 | User feedback | Assume: table+kanban for tenders; table+timeline for projects | Yes | Moe | 2025-12-27 | MVP UX.
U-034 | UI/UX | Mobile requirements (view-only vs full) | Low | 45 | Mgmt decision | Assume: responsive web; mobile later | No | Management | 2025-12-27 | Defer.
U-035 | Data | Unique IDs: project_code and tender_code format + constraints | High | 55 | Existing codes | Assume: preserve existing; create mapping for imports | Yes | PMO | 2025-12-27 | Import success.
U-036 | Data | Required fields for tender follow-up log | Med | 60 | Example log | Assume: who contacted, channel, outcome, next date, attachments | Yes | BD | 2025-12-27 | Quick win feature.
U-037 | Finance | Commercial confidentiality boundary between Finance and Engineering | High | 40 | Policy decision | Assume: engineering sees high-level fee totals only; finance sees breakdown | Yes | Management | 2025-12-27 | RBAC.
U-038 | HR | Timesheets expectation: do we track time per task? | Med | 45 | HR process | Assume: track time per task for cost centers (MVP optional) | Yes | HR | 2025-12-27 | Later module.
U-039 | BI | KPI definitions: tender win rate, cycle time, margin, utilization | High | 45 | KPI list | Assume: define KPIs in docs + calc formulas | Yes | Management | 2025-12-27 | Dashboards.
U-040 | Docs/RAG | Ground-truth evaluation: who scores summaries and how | Med | 50 | Eval rubric | Assume: 1–10 rubric + comments; weekly review | Yes | QA/QC | 2025-12-27 | Recursion loops.
U-041 | Docs/RAG | Hallucination controls: what is acceptable inference vs must-cite | High | 45 | Policy | Assume: anything contractual must cite; unknowns flagged | Yes | Compliance | 2025-12-22 | Critical.
U-042 | Ops | Approval workflow for tender submission package | High | 45 | SOP | Assume: discipline sign-off → PMO QA → VP approval | Yes | Management | 2025-12-27 | Workflow engine.
U-043 | Ops | What constitutes 'quality' tender: scoring rubric criteria | High | 40 | Management rubric | Assume: compliance, clarity, differentiation, methodology, visuals | Yes | Management | 2025-12-27 | Optimization mega project.
U-044 | Docs | Template repository location + access rights | Med | 55 | Current template folders | Assume: central templates vault with version control | Yes | PMO | 2025-12-27 | Governance.
U-045 | Ops | Standard response SLA to client emails | Med | 55 | Policy | Assume: 24h business days for external; 4h internal | Yes | Management | 2025-12-27 | Notification rules.
U-046 | AI Ops | Prompt/version management approach (registry) | Med | 55 | Decision | Assume: prompts/ folder + semantic versions + changelog | No | Engineering | 2025-12-27 | Implement soon.
U-047 | AI Ops | Model selection per task (summaries vs extraction vs codegen) | Med | 50 | Benchmarks | Assume: extraction uses deterministic settings; codegen separate | No | Engineering | 2025-12-27 | Optimize later.
U-048 | Compliance | Need for redaction before sending docs to LLMs | High | 35 | Policy | Assume: auto-redact PII/IDs for Restricted docs | Yes | Compliance | 2025-12-22 | High stakes.
U-049 | Compliance | Consent + lawful basis tracking for personal data in HR docs | High | 35 | Legal guidance | Assume: consent records stored; access logged | Yes | HR/Compliance | 2025-12-27 | PDPL alignment.
U-050 | Deployment | Backup + DR requirements (RPO/RTO) | High | 40 | IT policy | Assume: daily backups; RPO 24h; RTO 8h for MVP | Yes | IT Lead | 2025-12-27 | Production readiness.

## Assumptions_Log
ID | Assumption | Rationale | Risk_if_wrong | Validation_method | Status | Owner | Notes
A-001 | MCE needs 3 quick wins within 2 weeks: Project Tracker, Tender Tracker, Tender Optimization starter. | Vice Chairman request; visible value. | Scope creep delays MVP. | Confirm priorities in 30-min alignment. | Proposed | Moe | Lock sprint 0 backlog.
A-002 | Initial deployment will be Docker Compose on a single VM; CI/CD later. | Fastest to ship. | May conflict with IT standards. | Confirm with IT; check network + backups. | Proposed | IT Lead | K8s roadmap optional.
A-003 | Default doc classification is Confidential; Restricted for finance/PII/health. | Risk control. | Over-restrict may slow ops. | Agree classification policy + examples. | Proposed | Compliance | Align with PDPL/ADHICS.
A-004 | Email workflow will be draft-only (HITL send) in MVP. | Reduce risk. | Less automation benefit. | Mgmt approval; map SOP. | Proposed | Compliance | Later can automate sending.
A-005 | RAG indexing will be global with strict filters (tenant/project/role). | Simpler reuse across tenders. | Leak risk if filters fail. | Security review + red-team tests. | Proposed | Engineering | Add audit logs.
A-006 | Front-end: Next.js + shadcn/ui + TanStack Table; Back-end: FastAPI. | Speed + maintainability. | Team preference mismatch. | Spike in 1 day; verify toolchain. | Proposed | Engineering | Can swap UI lib.

## Requirements_Checklist
Area | Requirement | Priority | MVP | Acceptance_criteria | Notes
Project Tracker | Create/edit projects with stage, PM, start/end/DLP dates, % progress. | P0 | Yes | CRUD + list view + filters + export. | Core quick win.
Project Tracker | Milestone list + upcoming deadlines panel. | P0 | Yes | Shows next 10 milestones w/ T-x days. | Feeds alerts.
Project Tracker | Stage timeline (simple Gantt) + stage history. | P1 | No | Shows stage start/end; audit trail. | Phase 2.
Tender Tracker | Tender intake record w/ client, ref, deadline, status, value, team owners. | P0 | Yes | CRUD + list view + required fields validation. | Core quick win.
Tender Tracker | Countdown (T-x) + configurable thresholds + escalation. | P0 | Yes | Alerts fire at 14/7/3/1 days and day-of. | Critical.
Tender Tracker | Follow-up scheduler + comms log (who, when, outcome). | P0 | Yes | Next follow-up date; status notes; reminders. | Quick win req.
Tender Optimization | Upload tender pack (PDF/zip) + auto extract key dates/requirements. | P0 | Yes | Generates summary report + checklist in <5 min (small packs). | Starter PoC.
Tender Optimization | Discipline tagging (Arch/MEP/Struct/QS/General) + highlight needed reviews. | P0 | Yes | Outputs per-discipline brief + action list. | Delegation.
Tender Optimization | Auto draft participation/regret letter + RFI template. | P1 | No | Draft generated; HITL edits. | Phase 2.
Notifications | In-app notifications + email alerts with acknowledgements. | P0 | Yes | Ack required for critical; escalation if not acked. | MVP.
Security/RBAC | Roles: Super Admin, Chairman/VP, Dept Head, PM, Engineer, Finance, Viewer. | P0 | Yes | Role-based screens + data filters. | Non-negotiable.
Documents | Per-project folder templates + controlled sharing. | P0 | Yes | One-click project folder scaffold in storage. | MVP minimal.
RAG | Chunking + metadata index + retrieval UI (search + citations). | P1 | No | Search works w/ citations to source location. | After PoC.
Finance | Invoice/payment alerts + 30/60/90 dashboard from exports. | P1 | No | Reads CSV exports and shows forecast cards. | Phase 3.
HR | Resource planning: manpower by project + utilization. | P2 | No | Utilization dashboard + allocation table. | Later.
BI | Executive KPIs dashboard (projects, tenders, risks). | P1 | Yes | One page with core KPIs; charts.js. | MVP light.

## Document_Taxonomy
Doc_type | Examples | Sensitivity_default | Primary_use | Chunking_rule | Key_metadata_fields
Tender Pack | RFP/RFQ/RFI, Instructions to Tenderers | Confidential | Tender intake + requirements extraction | Hierarchical by headings; preserve tables | client, tender_id, deadline, rfi_due, scope_keywords, discipline_tags
Scope of Work | SoW sections, deliverables, milestones | Confidential | Delegation + compliance check | Chunk by SoW clauses; 300-700 tokens + overlap | deliverable_id, obligation_flag, acceptance_criteria, discipline
Commercial Terms | payment terms, bonds, penalties | Restricted | Risk + pricing strategy | Chunk by clause; keep amounts as structured fields | currency, amounts, penalty_type, due_dates
Contract/LOA | consultancy agreement, LOA, amendments | Restricted | Obligations + liabilities + timeline | Chunk by numbered clauses; cross-reference definitions | liability_type, indemnity, termination, governing_law
Technical Proposal (past) | methodology, organogram, CVs | Confidential | Template mining + quality scoring | Chunk by sections; extract reusable blocks | section_type, win_notes, differentiators
Commercial Proposal (past) | fees, breakdowns | Restricted | Benchmarking + pricing patterns | Chunk by tables; normalize rows | fee_items, rates, assumptions
Emails/Correspondence | client emails, subconsultant emails | Confidential | Task extraction + audit | Thread reconstruction; chunk per message + action items | sender, recipients, date, action_items, attachments
Meeting Minutes | kickoff minutes, site visit minutes | Confidential | Decisions + actions | Chunk by agenda item | decision, owner, due_date

## 2_Week_Plan
Day | Theme | Deliverables | Key_tasks | HITL_checkpoint
Day 1 | Repo + environment | Monorepo bootstrapped; Docker compose up | Create repo structure; choose template; run 'make dev' | Confirm stack + hosting
Day 2 | DB + Auth foundation | Postgres schema v0; RBAC skeleton | Prisma/Alembic; auth (JWT/session); seed roles | Confirm roles/permissions
Day 3 | Project Tracker MVP | Projects CRUD + dashboard v0 | API endpoints + UI table + filters | Validate fields/stages
Day 4 | Tender Tracker MVP | Tenders CRUD + countdown logic | Status workflow; follow-up reminders | Validate thresholds
Day 5 | Notification Engine | In-app + email alerts v0 | Scheduler + escalation; ack tracking | Choose channels
Day 6 | Tender intake upload | Upload PDF/ZIP + storage; doc parsing PoC | Docling pipeline; extract key dates | Validate extraction
Day 7 | Tender summary report v1 | Auto summary + checklist output | Generate report; export PDF/MD | Quality review
Day 8 | Discipline delegation v1 | Per-discipline brief + task list | Classifier rules; color tags; email drafts | Team usability
Day 9 | Hardening sprint | Audit logs + permissions tests | Add logging; add unit tests | Security review
Day 10 | Dashboard polish | Exec KPI page v0 | Charts; saved views | Mgmt acceptance
Day 11 | Data import | Import current projects/tenders from CSV | Mapping; validation | Data correctness
Day 12 | UAT week-start | Pilot with 3 users | Bug fixes; UX tweaks | Go/No-go
Day 13 | Deployment prep | Docker images + env configs | CI basic; backup notes | IT signoff
Day 14 | Demo + handover | Demo to Vice Chairman; backlog v2 | Training pack; next sprint plan | Approve roadmap

## Prompt_Library_Index
Prompt_ID | Name | When_to_use | Inputs | Outputs | Owner | Notes
P-001 | Repo Scout: inventory | When starting a new code/doc base | root_path, patterns | inventory.json + dedupe report | AI Agent | Run before any summarization.
P-002 | Doc Churn: normalize | Convert PDFs/docs/md to normalized md + metadata | files + taxonomy | normalized_md + metadata.yml | AI Agent | Use Docling; keep page refs.
P-003 | Chunk & Tag | Create chunks + tags + chunk_index | normalized_md | chunks/*.md + chunk_index.csv | AI Council | Must emit citations.
P-004 | Redundancy Killer | Merge duplicates; produce canonical spec blocks | chunk_index + chunks | spec_blocks/*.md + merge_log | Council Judge | HITL approve merges.
P-005 | Spec Builder | Build enterprise-ready technical spec from blocks | spec_blocks | /docs/spec/*.md | Chief Architect Agent | Includes NFRs + RBAC.
P-006 | MVP Builder | Generate tickets + micro-prompts for Claude Code | spec | /prompts/dev/*.md | PM Agent | One ticket per prompt.
P-007 | Tender Analyzer | From tender pack → summary + checklist + discipline briefs | tender pack | report.md + tasks.csv | Tender Council | Gated by HITL.